Planning Logic

A Sprint is a fixed period or duration in which a team works to complete a set of tasks.

An Epic is a big task or project that is too large to complete in one sprint. It is broken down into smaller tasks (stories) that can be completed over multiple sprints.

A Story is a small task. It is part of an Epic.

A Story Point is a number that represents how much effort a story takes to complete (usually in the form of a Fibonacci series).

•  1 — Very Easy task

•  2 — Normal task

•  3 — Moderate task

•  5 — Difficult task

Story point scale used: 1, 2, 3, 5

## Worked Example — Auto Ticket Classification Using Flow Designer

The example below uses the actual backlog for this project (see Project Planning Template).

Sprint 1

Environment Setup (Epic 1)

Create Update Set (USN-1)                         1

Create Incident WorkFlow table (USN-2)              3

Ticket Intake (Epic 2)

Build ticket submission form (USN-3)                2

Flow Trigger (Epic 3)

Configure "record created" trigger (USN-4)         2

Total Story Points in Sprint 1 = 1 + 3 + 2 + 2 = 8

Sprint 2

Automated Classification Logic (Epic 4)

Classify Network tickets (USN-5)                    2

Classify Hardware tickets (USN-6)                   2

Classify Access/Password tickets (USN-7)            2

Classify Performance tickets (USN-8)                2

Classify remaining tickets as General IT (USN-9)    1

Notification (Epic 5)

Send Email after classification (USN-10)            3

Testing & Validation (Epic 6)

Test flow and review execution details (USN-11)     3

Total Story Points in Sprint 2 = 2 + 2 + 2 + 2 + 1 + 3 + 3 = 15

## Total Story Points

Sprint 1 = 8

Sprint 2 = 15

Total Story Points = 8 + 15 = 23

No. of Sprints = 2

Velocity = Total Story Points Completed ÷ Number of Sprints

Velocity = 23 ÷ 2 = 11.5

Your team's velocity is 20 Story Points per Sprint (80 total story points planned across 4 sprints of 6 days each).